## Sheet1
Sprint Retrospective-1
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Finalized a meaningful and SDG-aligned project idea. | Delay in finalizing sensors due to scattered research. | Start with a requirement matrix for sensor selection. | Use a structured comparison table for sensor evaluation. | Prioritize hardware research before finalizing tech stack.
Smooth collaboration during idea finalization. | Documentation was initially vague in technical sections. | Begin writing documents parallel to the ideation phase. | Assign a documentation lead per sprint. | Maintain version-controlled documentation (Google Docs or Git).
Identified real-time application and demography relevance. | Unfamiliarity with sensor capabilities caused confusion. | Schedule internal sessions to study sensor datasheets. | Set aside a day for technical deep-dives each sprint. | Encourage everyone to go through sensor datasheets individually.
SDG alignment improved clarity and purpose of the project. | Some members struggled with time management | Implement a sprint board to visualize task assignments. | Use MS Planner or Trello to assign and track deliverables. | Daily/alternate-day sync-ups to ensure alignment.