## Sheet1
Sprint Retrospective-2
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
All four sensors were successfully integrated. | GSR readings were noisy and unstable in some conditions. | Calibrate GSR using dry and wet skin tests. | Include environmental testing sessions. | Test sensors under different temperatures and lighting.
Real-time data was successfully streamed to the serial monitor. | Temperature sensor readings varied slightly. | Add sensor warm-up time before capturing values. | Wait 10 seconds before initial temperature capture | Log all sensor data for trend analysis.
Heart Rate and SpO2 values matched expected clinical ranges. | Some issues with power draw when all sensors ran together. | Use a stable USB hub or external power source. | Measure board voltage output under load. | Don’t overload digital/analog pins.
Basic filtering helped improve output readability. | Serial monitor lag when all sensors outputted simultaneously. | Optimize the update frequency and serial baud rate. | Reduce unnecessary print statements. | Modularize sensor code for easy tuning.