## Sheet1
Sprint Retrospective-3
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Model was successfully deployed on the embedded device. | Limited memory on the microcontroller required model optimization. | Try quantizing the model further or using a simpler architecture. | Use float16 or int8 quantization during TFLite conversion. | Always check memory usage and model size before deployment.
Real-time predictions were accurate in most test scenarios. | Occasional lag in alert triggering. | Implement non-blocking code and optimize data processing flow. | Use interrupts or state machines for faster response. | Prioritize efficiency in alert mechanisms.
Hear attack risks were predicted successfully | False positives occurred when noise levels increased. | Add more data samples for training and improve preprocessing filters. | Collect more diverse training data and retrain the model. | Always validate sensor data before feeding it to the model.
All modules were integrated successfully. | Model debugging was difficult due to limited on-device logging. | Log more intermediate values to assist in debugging. | Print prediction probabilities and feature values in debug mode. | Maintain verbose logging during dev and switch to silent in production.