## Sheet1
Prioritize BLE Stack Development : Resolve BLE stack integration issues and test functionality with multiple devices. | Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | x | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Successful Data Collection : Real-time data from sensors (Heart Rate, SpO2, HRV, GSR, Temperature) was captured and processed successfully using the Arduino Nano 33 BLE Sense Rev2 | Bluetooth Connectivity Issues : Dependency issues with BLE stack integration caused delays in wireless health monitoring functionality. | Buffer for Scope Changes : Introduce a buffer period in future sprints to accommodate unexpected changes in requirements. | Prioritize BLE Stack Development : Resolve BLE stack integration issues and test functionality with multiple devices. | Conduct Daily Stand-Ups : Track progress and address blockers immediately.
ML Model Integration : The lightweight ML model trained using TensorFlow Lite was successfully integrated with the Arduino Nano 33 BLE Sense Rev2 , enabling on-device inference for real-time anomaly prediction. | UI Components Incomplete : User Interface components for alerts and health metrics visualization were not completed on time. | Dedicated Resources for BLE and UI : Allocate dedicated team members to focus solely on BLE stack development and UI design to prevent bottlenecks. | Allocate Dedicated Resources for UI : Finalize the design and implementation of the alert system and health metrics dashboard. | Finalize Requirements Before Sprint Starts : Ensure all requirements are locked before the sprint begins.
High Model Accuracy : Achieved 97% accuracy during ML training using neural networks on the synthetic_heart_attack_data_balanced.csv dataset. This high accuracy demonstrates the robustness of the model in detecting heart attack symptoms. | Scope Changes Mid-Sprint : Additional requirements (e.g., multi-sensor fusion algorithms) introduced mid-sprint led to scope creep and missed deadlines. | Early Code Reviews : Implement early code review checkpoints to identify integration blockers early in the sprint. | Setup Early Code Review Checkpoints : Conduct daily stand-ups and code reviews to monitor progress and address issues promptly. | Perform Rigorous Testing : Simulate real-world scenarios to validate the system's performance.
User study showed 87% would change behavior based on platform information | Urban Planning recommendations were sometimes too generic and not specific enough to local conditions | Optimize Arduino Nano 33 BLE Usage : Explore advanced features of the board, such as IMU for driver instability detection and low-power optimization. | Enhance ML Model Accuracy : Incorporate additional features (e.g., stress levels from GSR, temperature fluctuations) into the ML model for better prediction accuracy. | Learn from Past Mistakes : Regularly revisit the sprint retrospective document to implement improvements.
Hardware Compatibility : The Arduino Nano 33 BLE Sense Rev2 proved to be an ideal choice due to its TinyML support , BLE capabilities , IMU for driver instability detection , and low power consumption . | Sensor Calibration Challenges : Some sensors required recalibration to ensure accurate data collection, which consumed extra time. | Enhance Dataset Diversity : Incorporate more real-world data to improve the model's generalization and robustness. | Leverage Arduino Nano 33 BLE Features : Use the IMU (Inertial Measurement Unit) to detect sudden driver instability and integrate it with the ML model for improved anomaly prediction. | Utilize Arduino Nano 33 BLE Capabilities : Maximize the use of the board’s BLE, IMU, and TinyML capabilities for seamless integration and real-time health monitoring.